## Basic Gantt Chart
Report Timeline
| TASK NAME | START DATE | END DATE | START ON DAY* | DURATION* (WORK DAYS) | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
Draft report
| Review of ASHRAE level II reports | 2019-09-17 | 2019-09-23 | 0 | 7 | 10%
| Reasearch on audit results | 2019-09-23 | 2019-09-27 | 6 | 5 | 20%
| Compiling report outcomes | 2019-09-30 | 2019-10-04 | 13 | 5 | 40%
| GAP analysis | 2019-10-07 | 2019-10-14 | 20 | 8 | 60%
| Draft report submission | 2019-11-19 | 2019-11-22 | 63 | 4 | 80%
| Final report submission | 2019-12-20 | 2019-12-31 | 94 | 12 | 100%
Formulas:
DURATION* (WORK DAYS) = DATEDIF([START DATE],[END DATE],"d")+1

## Findings
reduce energy use and greenhouse gas (GHG) emissions |  |  |  |  | Building energy retrofits and new construction |  | Energy retrofits : 25% energy savings. Deep energy retrofits: 40% energy savings.
enhance occupant experience and improve service delivery to citizens |  |  |  |  | Leading Workplace Strategies (LWS)
lower costs to improve the province’s lifecycle return on investment |  |  |  |  | Electric vehicle charging equipment |  | 2040 no emission cars
Smart building technology
Adaptation for resilience
Clean energy supply
Reports Reviewed
Outcome
Unit | 11221 – Richard Blanshard |  | 2015 | 2016 | 2017 (partial) | After ECM implementation
Audit date | 2018-06-19 | Energy Use (GJ) | 17668 | 16115 | 11837 | 4773 GJ (39.50%), | ECMs recommended for implementation | 14 | Diposal and handling of old items
Occupied space | 23,291 sq.m | Energy Cost ($) | 293315 | 268564 | 288045 | 94118 | Negative NPV and implementation(lighting mostly) | 5 | LCA analysis for GHG emissions
|  | GHG Emissions (tCO2) | 81.9 | 76 | 56.7 | 23.28 tCO2 (32.31%).
Unit | 11809 - Vancouver Island Regional Correctional Centre |  | 2015 | 2016 | 2017 (partial) | After ECM implementation
Audit date | 2018-09-21 | Energy Use (GJ) | 13241 | 13957 | 12043 | 2,089 GJ (14.09%)
Occupied space | 13,715 sq.m | Energy Cost ($) | 262147 | 252567 | 216110 | 60691 | ECMs recommended for implementation | 19
|  | GHG Emissions (tCO2) | 329.7 | 353.7 | 310.9 | 29.71 tCO2 (7.48%) | Negative NPV and implementation(lighting mostly) | 4
Unit | 17871 – 22 Main St Provincial Court |  |  |  |  | After ECM implementation
Audit date | 2018-09-21 | Energy Use (GJ) |  |  |  | 5,503 GJ (43.97%),
Occupied space | 11,083 sq.m | Energy Cost ($) |  |  |  | 96470 | ECMs recommended for implementation | 22
|  | GHG Emissions (tCO2) |  |  |  | 180.19tCO2 (49.3%). | Negative NPV and implementation(lighting mostly) | 4
Unit | 30098 – Dalhousie Kamloops |  |  |  |  | After ECM implementation
Audit date | 2018-09-28 | Energy Use (GJ) |  |  |  | 1,304 GJ (30.14%),
Occupied space | 2,612 sq.m | Energy Cost ($) |  |  |  | 24212 | ECMs recommended for implementation | 18
|  | GHG Emissions (tCO2) |  |  |  | 48.98 tCO2 (37.18%). | Negative NPV and implementation(lighting mostly) | 3

## Sheet1
papers
energy auditing
increases occupants‘ comfort
there is a lack of economic analysis about the recommendations and results after energy audits.
Learning-by-doing spillovers.
It turns out that all three categories of explanations are theoretically sound and that limited empirical evidence exists for every category as well, although the empirical research is by no means consistently strong across all of the specific explanations
the energy efficiency and associated pricing of products on the market are economically efficient
Although the theory is clear, empirical evidence is—in general—quite limited.

## Table1
ID | Field1
1